## Slide 1
OPERATIONALISATION OF SREP
National Institute of Agricultural Extension Management Rajendranagar, Hyderabad
Dr. M.A.Kareem

## Slide 2: OPERATIONALISATION OF SREP SREP - operationalization process can be categorized into five areas namely- 1. Action Planning 2. Fund Flow Mechanism 3. Execution of Extension Programmes 4. Research Programs and 5. Monitoring of Filed Activities.

## Slide 3
A. Action Planning:
Action planning as a specific step in operationalising the strategies at grass root level (The strategies are long term in nature where as action plan draws out a systematic approach in realizing these strategies step by step).
Though strategies provide the possible future direction, action planning gives an outline of functional attributes in terms of what,when, where, who, (for) whom and how long with financial modalities.
The process of Action Planning is as follows:
  Project Director distribute copies of approved SREP to GB, AMC, BTT and FAC members of the district.
  2. BAP, DAP and SEWP are prepared based on SREP
  3. Stakeholders involvement in preparation of plans and they should be thorough with the intricacies of SREP.

## Slide 4
BTT members shall identify activities from SREP which are relevant to (AESs) and their block
3. SREP acts as a guiding force however BTT and FAC members shall take the following issues into consideration for preparing BAP
(a) Extension activities identified in SREP
(b) Group demands as identified by FAC members
(c) On going schemes for dovetailing
(d) Success stories identified for replication
These above dimensions need to be considered on annual/seasonal basis in the joint meeting of BTT and FAC at each FlAC for preparing BAP.

## Slide 5
4. FAC would approve this plan after incorporating necessary prioritized research and extension gaps. Convenor of BTT is responsible for sending the approved BAP to ATMA.
5. Project Director, ATMA shall organize AMC meeting and put-up the BAPs from all the blocks for technical scrutiny of their relevance as well as for dovetailing.

## Slide 6
P.D. would prepare its District level action plan based on the needs and priorities cutting across blocks boundaries and issues emanating out of SREP. However, PD ATMA must refer to the ‘Cafeteria of Activities’
7. The AMC scrutinize the BAPs and ATMA level action plan. This will form the basis for District Action Plan (DAP). AMC shall prepare this DAP by keeping funds availability in view.
8. Project Director shall organize GB for discussing DAP. GB will prioritize the issues in DAP depending upon the availability of funds and approve the DAP. GB ensures that there shall be equitable fund allocation across the blocks.
9. Project Director, ATMA shall send the approved DAP to State Nodal Officer for preparation of SEWP with the facilitation of SAMETI and
release of funds from GOI.

## Slide 7
B. Fund flow mechanism
As per the primary document circulated by GOI under X Plan Scheme ‘Support to State Extension Programmes for Extension Reforms”, based on the SEWP the funds would be placed with an autonomous institute at state level identified by the state for its onward transmission to SAMETI and ATMAs
  Once the district receives the funds, the same shall be passed
on to each FIAC for execution of field programmes. The fund will be placed in a bank account jointly operated by Chairman, FAC and Convenor BTT.
  2. During monthly or fortnightly meetings conducted at FIACs, BTT members would take advance to carryout the activities identified in BAP. The advance has to be realized immediately after completion of the activities for which it was taken or after 15 days whichever is earlier along with a brief report.

## Slide 8
3. Records like Cashbook, Proceedings register, Dead stock register etc. would be maintained at each FIAC by Convenor, BTT.
C. Execution of Extension Programmes:
Once the funds received by the Convenor, BTT, the field programmes need to be executed. While executing the field activities the following points are to be considered.
1. Awareness Campaign
2. Training
3. Demonstration
    4. Field Visits

## Slide 9
D. Execution of Research Programmes
1. Refer the researchable issues identified in SREP to Zonal Agricultural Research Extension Council (ZAREC) of Zonal Research Station (ZRS),
Scientific Advisory Committee (SAC) of Krishi Vigyan Kendra (KVK)
The issues that are already been addressed by SAU/ICAR or any other agencies shall be identified and communicated to ATMA for dissemination.
2. The issues which have not been addressed would be categorized into a.Long term researchable issues
b.Short term researchable issues
3. The long-term issues to be communicated to SAU, ICAR institutions for redressal and the short-term issues addressed to local research
institutions such as KVK and/or ZRS preferably through on-farm trials.

## Slide 10
BTT, FAC and AMC of ATMA would be involved in the On Farm Trials (OFTs), for execution and dissemination of proven technologies.
E. Monitoring of field activities:
Monitor block level and village level activities on monthly basis at FIAC level.
The progress made shall be reviewed during the first week of every month in the joint meeting of BTT and FAC members.
The Convener of BTT shall compile the progress reports of all line departments and submit to Project Director, ATMA
Review of progress of activities at district level by AMC.
During second week of every month after receipt of progress reports from the blocks GB shall review the progress every quarter

## Slide 11
Joint interaction workshop of GB and FAC quarterly.
For every quarter a joint interaction workshop, under the Chairmanship of Collector to create common thinking platform has to be conducted
4. The monitoring mechanism at state level include submission of quarterly reports, field inspections, workshops etc by Inter- Departmental Working Group (ID WG) convened by State Nodal Officer
Third party monitoring and evaluation – parameters shall be discussed separately for state level/ district level and block level activities.

## Slide 12
Thank you